MEMORANDUM

Phase 0 Reconciliation - Capstone Scope vs. Built Reality

| To: | Capstone Supervisor |
| --- | --- |
| From: | Wilsons Navid Wado Tiwa |
| Date: | 5 May 2026 |
| Re: | Reconciliation of Pre-Capstone proposal with built application; five decisions required |
| Window: | 2 months (target completion ~5 July 2026, 56 days) |
| Decision required by: | End of Sprint 1 (Day 7) |
| Read time: | ~10 minutes |

___________________________________________________________________________

1. Purpose

The Pre-Capstone proposal (docs/coursework/Major-assesment/) and the working application diverge in three load-bearing ways. Two further threads you raised - deepfakes and the CMU Africa Upanzi Network research on mobile money scams - are not yet incorporated. This memo:

States the gap honestly.

Proposes a single reframing that resolves all three divergences and absorbs both new threads.

Asks for sign-off on five specific decisions before Sprint 2 begins.

I am asking for sign-off so that I can stop revisiting the same scoping questions every week and spend the remainder of the two-month window on research, build, and pilot work.

2. What the Pre-Capstone Proposal Locked In

| Element | Proposal commitment |
| --- | --- |
| Pilot scope | Lagos, Nigeria + Douala, Cameroon (50 to 100 users) |
| Languages | English, French, Pidgin English (3) |
| Scam categories | 5 - advance-fee fraud, mobile money fraud, phishing, romance scams, identity theft |
| ML approach | Custom Scikit-learn / TensorFlow classifier trained on West African data |
| ML target | At least 85% classification accuracy |
| Risk-assessment SLA | 30 seconds via Firebase Cloud Function |
| Educational content | 20 or more articles in EN / FR / Pidgin English |
| Sample size | 50 to 100 users; 10 to 15 semi-structured interviews; SUS questionnaire |

3. What the Application Actually Is, Today

| Element | Built reality |
| --- | --- |
| Name | Rethicssec (folder still says rethicsai), v1.0.2+3 |
| Positioning | Cybersecurity Platform for Africa (pan-African) |
| Languages | 11 - en, sw, fr, ar, ha, yo, ig, zu, xh, af, sawa (Duala) |
| Features built | auth, dashboard, ai_assistant, incidents, cases, education, scanner, emergency, notifications, settings, admin |
| AI/ML layer | Vertex AI Gemini 1.5 Flash + OpenAI GPT-4o-mini via Firebase Cloud Functions |
| Custom-trained model | None |
| Measured accuracy | None |
| Fixed scam taxonomy in code | None - open-ended LLM threat analysis |
| Production state | Privacy Policy finalised; Play Store assets ready |

4. The Gaps, Scored by Risk

| # | Gap | Severity | Why it matters for the defense |
| --- | --- | --- | --- |
| G1 | Custom ML model promised but absent | Critical | Without it, "AI-powered" in the title is delivered entirely by third-party APIs. No evaluation, no accuracy claim, no contribution to the West African ML literature. |
| G2 | Pilot scope (Lagos+Douala) vs. app positioning (pan-African) | High | Pilot data will only validate two cities; broader claims will be unsupported by evidence. |
| G3 | 3 languages promised, 11 in app | Medium | More features than I can rigorously evaluate; risk of shallow multilingual claims. |

5. Two New Threads You Raised

5.1 Deepfakes

Operationally, AI-generated voice (vishing 2.0), video (romance and sextortion), and image (fake KYC documents) attacks are now in the wild against African mobile money users. Voice cloning targeting M-Pesa and MTN MoMo confirmations has been reported across East Africa.

For this capstone, however, detecting deepfakes is a different ML problem from classifying scam text. It would require audio or vision models, which is a separate research thread, not a tweak. The recommended posture is to treat deepfakes as a modular extension, not a pivot:

Add a sixth category, synthetic_media_fraud, to the text-only classification taxonomy. Even text-only classifiers can pick up the giveaway language ("listen to this voice note from your son").

Add one focused chapter section on the deepfake threat landscape in Africa, with audio/visual deepfake detection framed as Future Work.

Optionally, prototype one deepfake-aware UI feature (a "this audio looks AI-generated" warning) using an off-the-shelf detector.

5.2 CMU Africa Upanzi Network - mobile money scam research

This is the highest-leverage external thread in the entire memo. The Upanzi Network at CMU-Africa (Kigali) runs research that maps directly onto this project's needs:

Lamptey, Gueye, Luhanga, Seidu, Sowon (2024) - "A honeynet infrastructure to battle SMS scammers." Inexpensive honeynet collecting smishing messages from Rwanda, Botswana, Ghana, Kenya, Uganda.

Sowon et al. (2024) - "The Role of User-Agent Interactions on Mobile Money Practices in Kenya and Tanzania." IEEE Symposium on Security & Privacy 2024. 72 MoMo-user interviews.

"Mitigating Mobile Money Services Frauds in Rwanda" (2022). CMU-Africa authors.

"Security Gaps in the Mobile Money System in Rwanda: Challenges, Risks and Mitigation" (Springer 2024). Found the dominant attack types are SMishing, identity theft, phishing, and authentication attacks - corroborating four of our five categories with peer-reviewed evidence.

Implications for this capstone:

The Upanzi honeynet is, in effect, a working solution to my single biggest risk: labelled multilingual scam data.

I will email Assane Gueye and Karen Sowon in Sprint 1 with a one-paragraph academic data-sharing collaboration request - subject to Decision D4 below. Worst case: no reply. Best case: real-world data and a reference.

The Sowon S&P 2024 paper supersedes parts of my literature review and will be cited in the dissertation.

Position my contribution as victim-facing application + comparative ML evaluation, complementing the Upanzi Network's scam-collection infrastructure.

Given the 2-month window, the Upanzi data is best-effort, NOT on the critical path. The plan assumes their reply will not arrive in time.

6. Proposed Reframing - One Sentence

From: Build a custom ML classifier for West African scam detection.

To: Compare API-based LLMs against classical ML baselines for multilingual scam classification across the five categories in West Africa, deploy the chosen approach in a pilot mobile app in one West African city, and treat deepfake-modality detection as a modular extension.

This single reframing resolves all three gaps (G1 to G3) and absorbs both new threads:

| Element | How the reframing handles it |
| --- | --- |
| G1 - missing custom ML | Classical baselines are the contribution; LLMs become the comparison arm. |
| G2 - scope creep | Pilot stays in one West African city only; pan-African app is acknowledged as deployment infrastructure but not the unit of evaluation. |
| G3 - 11 langs vs 3 | Evaluation focuses on EN/FR/PCM; other 8 languages remain in the app as production features but are out of scope for accuracy claims. |
| Deepfakes | Added as 6th category for text-only detection of "voice note" / "video call" lures; full audio/visual detection deferred to future work. |
| CMU Africa | Upanzi work cited in lit review; honeynet dataset pursued in Sprint 1 best-effort; project positioned as complementary. |

7. Five Decisions I Need from You

| # | Decision | My recommendation | Tick |
| --- | --- | --- | --- |
| D1 | Adopt the LLM-vs-classical comparative reframing as the core ML contribution? | Yes |  |
| D2 | Lock pilot to ONE West African city (15 to 25 users) given the 2-month window; second city moves to Future Work? | Yes |  |
| D3 | Add synthetic_media_fraud as a sixth text-only category; defer audio/visual deepfake detection to Future Work? | Yes |  |
| D4 | Approve outreach to CMU-Africa Upanzi Network for academic data-sharing (best-effort, not on critical path)? | Yes |  |
| D5 | Update Chapter One Objective 2 to match the comparative-evaluation framing - replacing "at least 85% accuracy with custom classifier" with a comparative-evaluation objective? | Yes |  |

If any answer is no, the rest of the two-month plan changes materially. I would prefer to resolve all five in this first meeting.

8. Compressed Two-Month Sprint Plan (Post-Reframing)

The original proposal assumed a six-month plan. We have two. The app is already built, so most of that compresses cleanly. The pilot is the main scope cut.

| Sprint | Days | Focus | Exit gate |
| --- | --- | --- | --- |
| S1 - Foundation | 1-7 | This memo, supervisor sign-off, CMU outreach email sent, codebase recovery from 6-month dormancy, ML virtual environment, public datasets pulled (APWG, UCI SMS Spam, Kaggle phishing), PII masking, first labelled set (~500 examples). | TF-IDF + LR baseline running end-to-end; D1-D5 signed off. |
| S2 - ML core | 8-14 | Random Forest baseline; LLM zero-shot evaluation for Gemini 1.5 Flash and GPT-4o-mini; per-language confusion matrices on EN/FR/PCM; error analysis; dataset card and model cards. | Three-approach comparison table on held-out test set in ml/reports/. |
| S3 - App + pilot prep | 15-21 | Lock 6-category taxonomy in analyzeSuspiciousContent; log every classification (model, prompt, latency, output) to Firestore; deepfake-aware UI warning; consent forms, interview guide, recruitment plan, IRB submission if needed. | Scanner emits structured incidents tagged with category + confidence + model. Pilot kit ready. |
| S4 - Pilot launch | 22-35 | Pilot in ONE city only, 15 to 25 users (down from 50 to 100 across 2 cities); SUS + Firebase Analytics; 5 to 8 mid-pilot interviews. | Pilot wraps with usable data. |
| S5 - Analysis + writing | 36-49 | SUS scoring (Brooke 1996); thematic analysis (Braun and Clarke 2006); on-pilot ML accuracy via expert relabelling; chapters 4 (Results) and 5 (Discussion) drafted in parallel. | All analysis done; chapters 4 and 5 drafted. |
| S6 - Submit + defend | 50-56 | Polish, demo video, defense rehearsal. | Submitted, defended. |

8.1 What This Compression Cuts vs. the Original 6-Month Proposal

| Element | Original | Compressed |
| --- | --- | --- |
| Pilot users | 50-100 | 15-25 |
| Pilot cities | Lagos + Douala | One only (whichever is accessible) |
| Pilot duration | 8-10 weeks | About 2 weeks |
| ML baselines | 4 (TF-IDF x3 + transformer) | 2 (TF-IDF + LR; TF-IDF + RF) |
| Transformer fine-tuning | Yes (XLM-R / AfroXLMR) | Cut - too expensive in time |
| CMU-Africa data dependency | Plan assumed available | Send the email; assume no reply in time |
| Interviews | 10-15 | 5-8 |

8.2 Implication for D2 (Pilot Scope Decision)

D2 in section 7 originally read "lock pilot to Lagos and Douala only" in earlier drafts of this memo. With the two-month constraint, D2 is revised: pilot in one city only. I will confirm the city in Sprint 1 based on what is physically accessible. The other city is documented as future work in the dissertation.

9. What This Memo Does NOT Propose to Change

The mixed-methods research design in Unit 4 (still appropriate).

The annotated bibliography (will be extended, not redone - adding ~5 CMU-Africa citations and ~3 deepfake citations).

The Pre-Capstone proposal's literature review themes.

The Flutter + Firebase tech stack.

The Pre-Capstone proposal as a whole - it remains the foundation document; this memo is an addendum.

10. Key References Introduced by This Memo

Lamptey, B. O., Gueye, A., Luhanga, E., Seidu, M., & Sowon, K. (2024). A honeynet infrastructure to battle SMS scammers. CMU-Africa Upanzi Network. https://www.africa.engineering.cmu.edu/news/2024/10/10-smishing.html

Sowon, K., et al. (2024). The role of user-agent interactions on mobile money practices in Kenya and Tanzania. IEEE Symposium on Security & Privacy (S&P 2024). https://www.cylab.cmu.edu/news/2024/07/10-navigating-digital-financial-inclusion-in-africa.html

Mitigating mobile money services frauds in Rwanda (2022). CMU-Africa. https://www.researchgate.net/publication/364959459_Mitigating_Mobile_Money_Services_frauds_in_Rwanda

Security gaps in the mobile money system in Rwanda: Challenges, risks and mitigation (2024). Springer. https://link.springer.com/chapter/10.1007/978-3-031-62277-9_42

CyLab-Africa initiative - joint CMU CyLab + CMU-Africa. https://africa.engineering.cmu.edu/research/cybersecurity/cylab/index.html

Upanzi Network at CMU-Africa. https://www.africa.engineering.cmu.edu/research/upanzi/index.html